# NORTH & EAST YORKSHIRE RURAL HOUSING ENABLER NETWORK

# AGENDA ITEM NO: 3

# REPORT TO:	North & East Yorkshire Rural Housing Enabler Network

DATE:		7 February 2018

SUBJECT: 	           RHE Monitoring and Performance Q3 2017/18

# AUTHOR:		Colin Huby

1.0	 Purpose

1.1	To report on rural affordable housing delivery figures for 2017/18 up to the end of Q3 with any completions and consents in this third quarter. To list the number of rural enquiries in Q3 and to identify any of these enquiries for the Community Led Housing project.

2.0	Progress to date

Spreadsheets are attached showing detailed figures for the 2017/18 Programme.

# Monitoring matters agreed/adopted since the meeting in September 2017

At the N&EYRHE Network meeting held on 6th September 2017, discussions were held in relation to the confidence of the forecast completions to be achieved. It was noted that the majority of these were S106 units where RHEs had little control on these completions as they were reliant on sales. Suggestions were made about applying slippage parameters on developers to enable closer monitoring and to assist in identification of blockages.

# 3.0	N&EY Rural Delivery Programme 2017/18

# Rural Programme forecast completions for 2017/18 now total 225

Craven 6, Hambleton 29, Harrogate 63, Richmondshire 19, Ryedale 19,

Scarborough 0, Selby 73 and East Riding 19

(0 forecast completions are in the National Parks)

By RP (forecast):

Broadacres 52, Yorkshire 21, Harrogate HA 17, Accent 17, York HA 12,

Home Group 0, HBC 7, CDC 3, SDC 19, EYYC 7, Stonewater 16,

WDH 20, Together 17.

(10 Private Developer, 4 TBC, 3 CLH).

Type of site:

S106 168, Exception *12 and 100% AH not RES 45

Although only 1 exception site is included in this Programme, there are

several in the pipeline which are expected to be included in next year’s

Programme.

# The target is 100 per annum.

# At Q2 the forecast total was 281 across 40

schemes with the new forecast now at 225 across 32 schemes.

.

The RHEs have now reviewed the forecast list for Q4 so several schemes

not expected to complete before the end of March have now been taken

out of this current Programme. The changes are as follows;

In Craven, Giggleswick is not expected to complete.

In Harrogate, Melmerby, Knaresboro’ Rd Bishop Monkton and Tockwith

are all not expected to complete. Killinghall has been reduced from 9 to 8.

In Ryedale, the Black Swan Helmsley is not expected to complete and

Thornton Dale has been reduced from 9 to an expected 4.

In Scarborough, no units are expected to complete at West Ayton.

In East Riding, schemes at Flamborough, West Cowick, East Kilham,

Welton and Eastrington are all not expected to complete, however, two

schemes at Skirlaugh and Wilberfoss have over achieved.

In Richmondshire, another scheme at Gilling West is now expected to

complete this year so has been added to the Programme.

|  | Total | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- |
| Forecast affordable housing completions 17/18 | 225 | 23 | 36 | 44 | 122 |
| Actual affordable housing completions 17/18 |  | 21 | 19 | 67 | 3 |

2017/18 Quarter 3

# Forecast completions for Quarter 3 totaled 44

# Actual completions for Q3 totaled 67

# 5 in Hambleton, 10 in Harrogate, 3 in Richmondshire, 29 in Selby and

# 20 in East Riding.

# .

# N & EY Rural Enquires Q3

| Craven | 4 |
| --- | --- |
| Harrogate | 28 |
| Hambleton | 3 |
| Richmondshire | 2 |
| Ryedale | 1 |
| Scarborough | 2 |
| Selby |  |
| East Riding | 4 |
| Total | 44 |

# Out of the 44 rural enquiries for Q3, 7 are community led planning enquiries. These are as follows:

# East Riding – Hornsea, Driffield, Burstwick and Pocklington

# Hambleton - Exelby

# Richmondshire – Richmond Town, Leyburn

# The total number of completions so far for 17/18 at Q3 now stands at *110 which compares with a total of 131 at this time last year (16/17 Q3).

# *4 completions have completed early in Q4 so have been included in this total.

# Planning consents achieved by LA in 2016/17

# Planning consents forecast in 2017/18 total 1,376 units

Craven 46, Hambleton 4, Harrogate 822, Richmondshire 15, Ryedale 46, Scarborough 64, Selby 305 and East Riding 74

Q3 actual (outline)    =    20

Q3 actual (full)          =    26

Outline actuals for Q1/Q2/Q3 = 60 consents

Full actuals for Q1/Q2/Q3       = 100 consents

4.0       Future Milestones

The RHE Monitoring and Performance reports will continue to inform the

Network about delivery and future progress on a quarterly basis.

5.0	Recommendation

N&EYRHE Network members are requested to note and agree the following:

- Delivery to the end of Q3 for 2017/18 stands at  110

- Total forecast of rural completions (225) for the 2017/18 RHE Programme (by LA and RP breakdown of units).

- Total forecast of rural planning consents (1376) for the 2017/18 RHE Programme with (60) actual outline consents up to the end of Q3 and (100) actual full consents up to the end of Q3.

- 44 rural enquiries for Q3 with 7 of these Community Led Planning enquiries.