# NORTH YORKSHIRE RURAL HOUSING ENABLER NETWORK

# AGENDA ITEM NO: 3

# REPORT TO:	North Yorkshire Rural Housing Enabler Network

DATE:		14 October 2015

SUBJECT: 	           RHE Monitoring and Performance 2015/16

# AUTHOR:		Colin Huby

1.0	 Purpose

1.1	To report on rural affordable housing delivery for 2015/16 up to the end of Q2 with any completions and consents in this second quarter. To list the number of rural enquiries for Q2.

2.0	 Progress to date

Spreadsheets are attached showing detailed figures for the 2015/16 Programme.

# Monitoring matters agreed/adopted since the meeting in July 2015

At the NYRHE Network meeting held on 15th July 2015, it was agreed that

the target for completions should be increased from 75 per annum to 100

affordable units per annum.

# 3.0	NY Rural Delivery Programme 2015/16

# Rural Programme final forecast completions for 2015/16 total 204

Craven 33, Hambleton 73, Harrogate 27, Richmondshire 30, Ryedale 15,

Scarborough 10 and Selby 16.

(15 completions are in the NYM National Park and 2 units in the YDNPA)

By RP:

Broadacres 90, Yorkshire 20. Together 14, Home 45, Wakefield DH 16,

North Star 10, Stonewater 2 and HBC 2.

By non-RP:

Private developers (Estate) 5 in Ryedale.

Type of site:

S106 121, Exception 50 and 100% AH not RES 33

# The target is 100 per annum.

# At the July Network meeting the forecast total was 210 across 19

schemes with the final figure now at 204 across 18 schemes.

In Hambleton 2 units were withdrawn at Hackforth.

In Richmondshire 6 units were added at Leyburn.

In Ryedale 10 units were withdrawn from Kirkbymoorside

|  | Total | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- |
| Forecast affordable housing completions 15/16 | 204 | 47 | 10 | 42 | 105 |
| Actual affordable housing completions 15/16 |  | 47 | 12 |  |  |

2015/16 Quarter 2

# Forecast completions for Quarter 2 totaled 10

# Actual completions for Q2 totaled 12

# 4 in Hambleton, 6 in Richmondshire and 2 in Harrogate

# NY Rural Enquires Q2

| Craven | 6 |
| --- | --- |
| Harrogate | 20 |
| Hambleton | 4 |
| Richmondshire | 0 |
| Ryedale | 1 |
| Scarborough | 1 |
| Selby | 6 |
| Total | 38 |

# The total number of completions now stands at 59 which compares with a total of 37 at this time last year.

# Planning consents achieved by LA in 2015/16

# Planning consents achieved in 2015/16 total 795 units

Craven 99, Hambleton 32, Harrogate 419, Richmondshire 53, Ryedale 39, Scarborough 44 and Selby 109

Q2 forecast = 131

Q2 actual    =  46

|  | Total | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- |
| Forecast planning consents 15/16 | 795 | 79 | 131 | 366 | 215 |
| Actual planning consents15/16 |  | 105 | 46 |  |  |

4.0       Future Milestones

The RHE Monitoring and Performance reports will continue to inform the

Network about delivery and future progress on a quarterly basis.

5.0	Recommendation

NYRHE Network members are requested to note and agree the following:

- Delivery to the end of Q2 for 2015/16 stands at ( 59 )

- Total forecast of rural completions (204) for the 2015/16 RHE Programme (by LA and RP breakdown of units).

- Total forecast of rural planning consents (795) for the 2015/16 RHE Programme with (151) actual consents up to the end of Q2.